## Product Backlog
PRODUCT BACKLOG [Sprint 1]
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Search - Keywords: As a customer, I want to search for a product using keywords, so that I can quickly find the item that I'm looking for. | Jyoti Kundu | High | 3 | To Do
2 | Search - Category: As a customer, I want to browse different categories, so that I can explore a range of offerings from stores close to me. | Jyoti Kundu | High | 3 | To Do
3 | Search - Viewing an item: As a customer, I want to view an item's information, so that I can make an informed decision whether to purchase it. | Jyoti Kundu | High | 2 | To Do
4 | Sorting results by price: As a customer, I want to sort the search results from cheapest to most expensive, so that I can choose from the cheaper options first. | Jyoti Kundu | High | 3 | To Do
5 | Cart: As a customer, I want to view my cart, so that I can check what Items I'm missing or need to remove before checking out. | Jyoti Kundu | High | 5 | To Do
6 | Adding an item to the cart: As a customer, I want to add an item to my cart, so that I can purchase it together with other items. | Jyoti Kundu | Medium | 2 | To Do
7.1 | Selecting delivery options: As a customer, I want to be able to pick from a wide range of delivery options such as standard, express and same-day, so that I can select the best option that suits my needs. | Jyoti Kundu | Medium | 3 | To Do
7.2 | Selecting delivery options: As a customer, I want to designate a preferred window of time for my delivery to arrive, so that my delivery does not arrive when I am away from the house. | Jyoti Kundu | Medium | 3 | To Do
8 | Checkout: As a customer, I want to check out my order, so that I can pay and receive my order. | Jyoti Kundu | Medium | 3 | To Do
9 | Notification preferences: As a customer, I want to customise my notification preferences, so that I can select what I receive notifications for. | Jyoti Kundu | Medium | 2 | To Do
10 | Notifications - special offers: As a customer, I want to promptly receive notifications about special offers, so that I can take advantage of promos before they expire. | Jyoti Kundu | Medium | 2 | To Do
11 | Favoriting an item: As a customer, I want to favorite an item, so that I can be notified when there is a promo or discount for the selected item. | Jyoti Kundu | Medium | 2 | To Do
12 | Registration: As a new customer, I want to create an acount, so that I can save my personal details for future purchases. | Jyoti Kundu | Low | 3 | To Do
13 | Logging in: As a registered customer, I want to log in to my account, so that I can access my account and make purchases. | Jyoti Kundu | Low | 1 | To Do
14 | Personal detals (Profile): As a registered customer, I want to edit my personal details (name, address etc.), so that I can quickly check out my future purchases. | Jyoti Kundu | Low | 1 | To Do
15 | Definition of done: [Applies to all user stories] - Code is written by multiple developers and/or peer reviewed - Unit tests cover 80% of situations, and all tests pass - Functional testing based on acceptance criteria pass - Implemented feature is intuitive to use, and passes usability tests - Code tested and verified to work on website browsers (Chrome and Firefox), using Windows - Code contains no known bugs - Code is well-documented - Code approved by product owner

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Search - Keywords: As a customer, I want to search for a product using keywords, so that I can quickly find the item that I'm looking for. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Search - Category: As a customer, I want to browse different categories, so that I can explore a range of offerings from stores close to me. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Search - Viewing an item: As a customer, I want to view an item's information, so that I can make an informed decision whether to purchase it. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Sorting results by price: As a customer, I want to sort the search results from cheapest to most expensive, so that I can choose from the cheaper options first. | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Cart: As a customer, I want to view my cart, so that I can check what Items I'm missing or need to remove before checking out. | #N/A | #N/A | #N/A | #N/A | #N/A
6 | Adding an item to the cart: As a customer, I want to add an item to my cart, so that I can purchase it together with other items. | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Selecting delivery options: As a customer, I want to be able to pick from a wide range of delivery options such as standard, express and same-day, so that I can select the best option that suits my needs. | #N/A | #N/A | #N/A | #N/A | #N/A
8 | Selecting delivery options: As a customer, I want to designate a preferred window of time for my delivery to arrive, so that my delivery does not arrive when I am away from the house. | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Checkout: As a customer, I want to check out my order, so that I can pay and receive my order. | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Notification preferences: As a customer, I want to customise my notification preferences, so that I can select what I receive notifications for. | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Notifications - special offers: As a customer, I want to promptly receive notifications about special offers, so that I can take advantage of promos before they expire. | #N/A | #N/A | #N/A | #N/A | #N/A
12 | Favoriting an item: As a customer, I want to favorite an item, so that I can be notified when there is a promo or discount for the selected item. | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Registration: As a new customer, I want to create an acount, so that I can save my personal details for future purchases. | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Logging in: As a registered customer, I want to log in to my account, so that I can access my account and make purchases. | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Personal detals (Profile): As a registered customer, I want to edit my personal details (name, address etc.), so that I can quickly check out my future purchases. | #N/A | #N/A | #N/A | #N/A | #N/A
16 | Definition of done: [Applies to all user stories] - Code is written by multiple developers and/or peer reviewed - Unit tests cover 80% of situations, and all tests pass - Functional testing based on acceptance criteria pass - Implemented feature is intuitive to use, and passes usability tests - Code tested and verified to work on website browsers (Chrome and Firefox), using Windows - Code contains no known bugs - Code is well-documented - Code approved by product owner | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A