## Sheet1
| Features |  |  | Classic Burndown Chart - Sprint 1
|  | User Story | Estimate | Weeks | Day | Ideal Burndown | Remaining effort | PBI's completed that day
Blocked | PBI 1 | Search - Category | 3 | Before the start | 0 | 31 | 31
| PBI 2 | Sorting results by price | 3 | Week 1 | 1 | 28.93 | 31 | Nothing: 0
| PBI 3 | Favoriting an item | 2 |  | 2 | 26.86 | 31 | Nothing: 0
| PBI 4 | Registration | 3 |  | 3 | 24.79 | 31 | Nothing: 0
| PBI 5 | Logging in | 1 |  | 4 | 22.72 | 31 | Nothing: 0
| PBI 6 | Personal details (Profile) | 1 |  | 5 | 20.65 | 31 | Nothing: 0
|  | Sub-total | 13 | Week 2 | 6 | 18.58 | 31 | Nothing: 0
Kept | PBI 7 | Search - keywords | 3 |  | 7 | 16.51 | 31 | Nothing: 0
| PBI 8 | Viewing an item | 2 |  | 8 | 14.44 | 18 | Meeting with Product Owner; removed PBI's 1-6 [Total: 13]
| PBI 9 | Cart | 5 |  | 9 | 12.37 | 18 | Nothing: 0
| PBI 10 | Adding items to cart | 2 |  | 10 | 10.3 | 18 | Nothing: 0
| PBI 11 | Selecting delivery options | 3 | Week 3 | 11 | 8.23 | 18 | Nothing: 0
| PBI 12 | Checkout | 3 |  | 12 | 6.16 | 18 | Nothing: 0
|  | Sub-total | 18 |  | 13 | 4.09 | 18 | Nothing: 0
|  | Total | 31 |  | 14 | 2.02 | 13 | Completed PBI's 7, 8 [Total: 5]
[5 empty] | 15 | 0 | 0 | Completed PBI's 9, 10, 11, 12 [Total: 13]
|  | Ideal burndown rate: | 2.0667