## Sheet1
| Features |  |  | Classic Burndown Chart - Sprint 1
|  | User Story | Estimate | Weeks | Day | Ideal Burndown | Remaining effort | PBI's completed that day
Blocked | PBI 1 | Search - Category | 3 | Before the start | 0 | 31 | 31
| PBI 2 | Sorting results by price | 3 | Week 1 | 1 | 28.93 | 31 | Nothing: 0
| PBI 3 | Favoriting an item | 2 |  | 2 | 26.86 | 31 | Nothing: 0
| PBI 4 | Registration | 3 |  | 3 | 24.79 | 31 | Nothing: 0
| PBI 5 | Logging in | 1 |  | 4 | 22.72 | 31 | Nothing: 0
| PBI 6 | Personal details (Profile) | 1 |  | 5 | 20.65 | 31 | Nothing: 0
|  | Sub-total | 13 | Week 2 | 6 | 18.58 | 31 | Nothing: 0
Kept | PBI 7 | Search - keywords | 3 |  | 7 | 16.51 | 31 | Nothing: 0
| PBI 8 | Viewing an item | 2 |  | 8 | 14.44 | 18 | Meeting with Product Owner; removed PBI's 1-6 [Total: 13]
| PBI 9 | Cart | 5 |  | 9 | 12.37 | 18 | Nothing: 0
| PBI 10 | Adding items to cart | 2 |  | 10 | 10.3 | 18 | Nothing: 0
| PBI 11 | Selecting delivery options | 3 | Week 3 | 11 | 8.23 | 18 | Nothing: 0
| PBI 12 | Checkout | 3 |  | 12 | 6.16 | 18 | Nothing: 0
|  | Sub-total | 18 |  | 13 | 4.09 | 18 | Nothing: 0
|  | Total | 31 |  | 14 | 2.02 | 13 | Completed PBI's 7, 8 [Total: 5]
[5 empty] | 15 | 0 | 0 | Completed PBI's 9, 10, 11, 12 [Total: 13]
|  | Ideal burndown rate: | 2.0667

## Sheet1 (2)
Features |  |  | Done | Classic Burndown Chart - Sprint 1
PBI1 | Write user stories for remaining Sprint | 3 |  | Weeks | Day | Ideal Burndown | Remaining effort | PBI's completed that day
PBI2 | Maintain Scrum Meetings and Documentation | 8 |  | Before the start | 0 | 58 | 58 | Nothing: 0
PBI3 | Update Product Backlog | 2 |  | Week 1 | 1 | 54.13 | 53 | PBI1, PBI 3 [5]
PBI4 | Prioritize Backlog based on product owner meeting | 1 |  |  | 2 | 50.26 | 48 | PBI 5 [5]
PBI5 | Write test cases and definition of done for each feature | 5 |  |  | 3 | 36.26 | 34 | Completed: PBI 4 [1] Blocked: PBI 10-15 [13]
PBI6 | Add validation tests and document test results | 5 |  |  | 4 | 33.4708 | 34 | Nothing: 0
PBI7 | Implement enhancement feature | 5 |  |  | 5 | 30.6815 | 34 | Nothing: 0
PBI8 | Refactor code and rerun all tests | 8 |  | Week 2 | 6 | 27.8923 | 34 | Nothing: 0
PBI9 | Add continuous deployment | 8 |  |  | 7 | 25.1031 | 34 | Nothing: 0
[5 empty] | 8 | 22.3138 | 34 | Nothing: 0
[5 empty] | 9 | 19.5246 | 34 | Nothing: 0
| Blocked |  |  |  | 10 | 16.7354 | 34 | Nothing: 0
PBI 10 | Search - Category | 3 |  | Week 3 | 11 | 13.9462 | 34 | Nothing: 0
PBI 11 | Sorting results by price | 3 |  |  | 12 | 11.1569 | 34 | Nothing: 0
PBI 12 | Favoriting an item | 2 |  |  | 13 | 8.3677 | 34 | Nothing: 0
PBI 13 | Registration | 3 |  |  | 14 | 5.5785 | 13 | PBI2, PBI 6, PBI 8 [21]
PBI 14 | Logging in | 1 |  |  | 15 | 0 | 8 | PBI7 [5]
PBI 15 | Personal details (profile) | 1
| Sub-total | 13
| Total | 58
| Ideal burndown [1] | 3.8667
| Ideal burndown [2] | 2.7892